## Sheet1
Estimate Project Schedule
Project Start | 2021-10-01
|  |  | 2021-10-01 | [6 empty] | 2021-10-08 | [6 empty] | 2021-10-15 | [6 empty] | 2021-10-22 | [6 empty] | 2021-10-29
|  |  | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31
Task | Start | End | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1. Analysis
Task 1.1 Analyze the project scenario | 2021-10-01 | 2021-10-02
Task 1.2 Analyze the provided source code | 2021-10-02 | 2021-10-02
Task 1.3 Analyze Database and Schema | 2021-10-04 | 2021-10-05
Task 1.4 Analyze Application and Structure of Source Project | 2021-10-06 | 2021-10-07
2. Design
Task 2.1 Analyze Project Desing | 2021-10-08 | 2021-10-12
Task 2.2 Analyze Application Source Design | 2021-10-13 | 2021-10-20
Task 2.3 Analyze Interface Design | 2021-10-21 | 2021-10-31